## Evalution citeria
Assignment evalution citeria
1 | Articulate the requirements as a set of 'user experiences
2 | Compute the story Points
3 | Estimate the size and effort for the project.
4 | Understand and evaluate the importance of Sprint Ceremonies and Scrum roles and responsibilities in accordance to sprint execution
ASP Group 11
| Group members | BITS ID | Role play
| Ashish Ranjan | 2021ct93023@wilp.bits-pilani.ac.in | SM
| Rashi Chaudhary | 2021ct93024@wilp.bits-pilani.ac.in | PO
| Ritu Bala Rai | 2021CT93003@wilp.bits-pilani.ac.in | DEV
| Sandya Shanmugham | 2021CT93031@wilp.bits-pilani.ac.in | QA

## Case Study 1 Facify-me
Facify-me
User registration / Registration page
UI page / Login page / Registration page
Backend DB
Business logic: Validate the input, check the access level
Facify-me app home page
Dashboard summary no of games, teams wins, next match, Team details, Available slots for Ground
Book the grounds
Facility Admin, two Executives approvals Approval by mail, need to be stored in DB
Ground Availability
Ground list should only show Available / Free ground list at the time of
booking by multiple Admins
Ground should be made automatically available when the schedule is cancelled
Each ground should show Four slots (Schedule)
Up on every schedule confirmation respective team members and
coaches should get a notification on their mobile application
SMS system third party
Change request
Coach should be able to make request for any changes in ground
selection or Schedule changes
The request for change in Ground and Schedule should pass through the approval from Facility Admin Team and any of Two Executive
Scrum Role
Rashi- Scrum Master
Ashish - Product Owner
Ritu - Dev
Sandya - QA
Infrastructure set up
Intergration testing
Deployment

## Facify-me_BacklogUserstories
Module | Details | User Stories | Acceptance Criteria | Story point
1. Facify-me home page | i) Navigation bar with necessary details. | 1.1) Create homepage for facify-me app which will have navigation bar with required tabs/dropdowns. Description – facify-me homepage navigation bar should contain the following tabs/dropdowns : i) It should contain About us dropdown which will have contact us/team wins/ our achievements option ii) login/logout tab. | Acceptance Criteria – Homepage created with the navigation bar containg the required tabs/dropdown.
| ii) Dashboard summary no of games, teams wins, next match, Team details, Available slots for ground | 1.2) Create GUI frame for homepage of facify-me app with the necessary dashboard contents. Description – facify-me homepage should contain the different cards with following contents : i) Display the Dashboard summary. ii) Team Details/Team wins. iii) Number of matches organized by facify-me. iv) Total count of countries where we organize the event. v) Ground Details - It will contain available slots. | Acceptance Criteria - All required cards are successfully created and displayed in dashboard.
| iii) Backend functionaliy. | 1.3) Implement backend functionaliy(only for next available slots of ground) using get method to fetch the details from required table based on the differnt card contents. | Acceptance Criteria- Succesfully able to display the next available ground details.
2. Registration Module | Registration page will be accessed by Admin only. Admin will have the access to register the members. | 2.1) Create Registration webpage for each Member with their access_groups name and only general admin can access this page to add the other members details. i) Input fields – Member_Name, Age, DOB, Gender, Access_group, Country, Contact_No, Email_Id, Password, Confirm_Password. If access_group name is Player/Coach then one extra input field is mandatory i.e. Team_Name. ii) Button – Create Register Button at bottom of registration page. | Acceptance Criteria – Registration Page created with required input fields and validations.
| Perform the required validations on input field. All the fields are mandatory except team_name which is only mandatory where access_group is player/coach. | 2.2) Registration page input field should have proper input validations. i) All fields are mandatory. ii) DOB – YYYY/MM/DD iii) Email – abc@xyz.com iv) Password – a) Maximum 7 characters. b) both cases should be present with at least one special characters and digit. v) Confirm Password - It should match with the password field value. vi) If access_group is player/coach then team_name field is mandatory. vii) Button should be enable only when all fields are successfully validated. | Acceptance Criteria – Input fields validated for registration page.
|  | 2.3) Create table for member details in database. i)Table Name: member_details. Column names: i) user_name – varchar(2) – Len60 ii) gender – varchar(2) – Len60 iii) age – number iv) password - varchar(2) – Len60 (should be in encrypted form) v) access_group – varchar vi) email_id - varchar vii) contact - number viii) team_name - varchar (only for users where access_group field is player/coach). | Acceptance Criteria – New table created with required columns for team details.
| Front end and backend connectivity logic. | 2.4) Create backend logic and implement post method to send the regisration details to backend table. | Acceptance Criteria- User successfully able o register and the user details are successfully inserted into the table.
3. Login Page | Login page will contain forgot password/reset password functionality. | 3.1) Create login page with two input fields userid and password. Login button will enable only when both userid and password is submitted. 3.2) Create backend logic to implement any secure login technology(example JWT) . 3.3) Create forgot password page where user need to give user id, old password , new password and confirm new password and click on the submit button. 3.4) After clicking on the submit button password needs to be updated in the table. | Acceptance Criteria- Successfully able to login or reset the password.
4. Content Editor page | Facility Admin should be able to insert and edit the shedule details and update the results of the matches | 4.1 Create front end form with all required fields to capture the schedule details , match fixtures ,results and scores 4.2 Validate the fields , and busniess logic to validate the team schedule 4.3 Ensure there will be only 4 slots will present per ground business logic | Acceptance Criteria- Admin successfully able update the content and the match details are successfully inserted/updated into the table.
5. Ground Details | Required ground details will be inserted/updated by the admin. | 5.1 Create a form to insert the ground details and make ensure there will be maximum four slots will be present and this form should have submit button which will be enable only after all mandatory details will be populated successfully and make sure this page will be only accessible by admin. 5.2 Create a table in db which will store all ground related details. 5.3 Create business logic for validation and insert/update the data into the db. | Acceptance Criteria- Successfully inserted the data of ground details in db by admin.
6. Booking Ground | Ground details will be shown in form of grid with the book/Cancel button for each ground details. | 6.1 Create a web page for showing the ground details such as ground name, ground location, ground status(available/booked/waiting for approval), team name if a ground is booked and . 6.2 Create booking/Cancel button that will be only visible to access_groupis admin. 6.3 Create a business logic to fetch/update the details from/to the DB and trigger the mail to 5 executives. | Acceptance Criteria- Admin successfully able to send booking/cancel requests of ground and all relevant ground details are displayed in the ground availability page. Successfully mail will be trigerred after clicking on booking/cancel button.
7. Change Request | Create Web Page to show the booked ground details to coach so, that he can raise the request for changing the slot. | i) Create a web page to show the the booked ground details and a button to change the slot request. ii) Create a business logic so that if coach will click on change request button coach needs to select a specific new slot from dropdown (hidden unless the change button is clicked on). | Acceptance Criteria - Successfully able to raise the change request.
8. SMS functionality | Create business logic so that after booking/cancelling/change in slot sms will be sent to the respective person | Create business logic to check the approval count of executives if it is equal to 2 then approved sms/mail will be sent to the team members/coach. | Acceptance Criteria- SMS/Mail successfully sent after approval of two executive.

## Facify-me_Agile_Ceremonies
Sl.No | Ceremonies | Benefits | Schedule
1 | Sprint Planning | »Essential preceding ritual of every sprint »Ensures items are transferred from the product backlog to the sprint backlog, ensuring they are ready to commit to the completion | These usually last for two hours as per each week that will go into the sprint or First day of sprint /last day of previous sprint
2 | Daily Stand-Up | »Team members discuss any obstruction in their work process and also report on their daily progress. »Extremely helpful to keep the team members encouraged on the path of success and improvement. | Last for around 15 minutes of regular daily short meetings
3 | Backlog Grooming | »Product owner helps the Scrum team with prioritizing the order of the product backlog. »Members identify what needs to be added as well as root out defective or outdated items which need to be eliminated from the list. | Doesn’t really have to be fixed schedule or frequency Product owners call's to fix the frequency of shedule
4 | Sprint Review | » Scrum team demonstrates the work done to the PO and the stakeholders present » Feedback and relevant new business context is discussed upon, and finally the updating of the product backlog according to how the discussion proceeds. | Towards the end of the sprint ,usually last for around two hours or lesser depends on sprints size.
5 | Sprint Retrospective | » Identifies the opportunities and finally creating a plan as to how certain improvements can be brought upon in the upcoming sprint. » Discusses stronger points of the sprint and continue to apply them in upcoming sprints » Team members try to work on their efficiency of work and their delivered quality. | Usually last for 45 minutes as per each week that went into the sprint or end of the sprint